## 90-Day
Transfer Partnership Strategy
90-Day Cycle Action Planning Worksheet |  |  |  | Institutional Partners:
Austin Community College (ACC) and Texas State University (TxSt)
What is our charter for this 90-day cycle? (What are we going to accomplish?) |  |  |  | How will this accelerate progress on our SMART goal? How will we know?
Align math requirements and program maps for the top 10 programs at TxSt into which ACC students transfer |  |  |  | TXST
30 | ACTIVITIES | OWNER | 2-YR NEEDS/IMPLICATIONS |  | 4-YR NEEDS/IMPLICATIONS | DUE DATE | STATUS
| ) Program chairs/leads clarify and confirm the math requirements as identified by TXST for the top 12 majors. | Charles, Gaye Lynn, Dann | Requires additional discussion |  | Requires additional discussion | 6/24/2020;additional discussion on 7/22/2020 | Faculty have reviewed and provided feedback; some clarification needed for chart specific to Texas State University requirements with ACC requirements; discussed adding Health Science Majors as #13; Matt Brooks chair
| 2) A clear, concise document is created to share with advisors and students. | Shasta, Renee, Stephanie | Discussion will continue to have cross reference of requirements to share with advisors and others |  | Discussion will continue to have cross reference of requirements to share with advisors and others | 6/24/2020; additional discussion on 7/22/2020 | Need discussion and a draft document to show advising elements for Texas State
| 3) Begin exploration of the Blackboard shell for students declaring intent to transfer to TXST. | Renee and others | Renee continues to develop the shell; will share initial format with everyone when it is available |  |  | 6/24/2020;additional discussion on 7/22/2020 | Renee has started development; will share update and draft; will be called Transfer 101
| 4) Gather feedback on the college prep course to share at next meeting. | Dann, Gaye Lynn | Math chairs will discuss |  | Math chairs will discuss | 6/24/2020; additional discussion on 7/22/2020 | Need contact between two chairs for discussion; ACC has adopted multiple measures and will send to Dann Brown
60 | ACTIVITIES | OWNER | 2-YR NEEDS/IMPLICATIONS |  | 4-YR NEEDS/IMPLICATIONS | DUE DATE | STATUS
| Distribute the math requirement document and send information to Dana Center to update online information | to be identified |  |  |  | 2020-08-26 | The document with the math requirement for the two-year and 4-year degrees is still under discussion. Hopefully it will be completed in October and the group can finalize the requirements for use by advisors and students. The document is still under discussion. The team discussed using the document to create a simplified document for use in advising and in the mapping process.
| 2) Develop plan for developing and implementing the Transfer Blackboard shell | to be identified |  |  |  | 2020-08-26 | Renee has done significant work on the shell. An update will be provided in Ocstober. The group may discuss when it may be shared with students. Discussion was limited but work continues and 118 students have joined. Thanks again to Renee for the work.
| 3) Continue discussion to Determine if the college prep course will be shared by ACC and TXST | to be identified |  |  |  | 2020-08-26 | Chairs have not had discussion. The two math chairs agreed to discuss this topic.
| 4) Begin development of process for mapping the requirements for the 12 majors (associate and baccalaureate degrees) | Susie Tomason and Mary Jane with Stephanie |  |  |  |  | Three programs have been mapped, as pilot, for Bus. Adm., Elect. Eng., and Biology. The group briefly discussed the process. Some considerations for discussion: * Process that includes the requirements for the 4-year degree, * how to include foreign language requirement and other "notes" in map, * Gary will discuss AAS to BAAS program process and map with Dean & Advising Center; WI requirement may be separate discussion consideration. Following discussion, a small group will review the process to simplify and discuss at the next meeting.
90 | ACTIVITIES | OWNER | 2-YR NEEDS/IMPLICATIONS |  | 4-YR NEEDS/IMPLICATIONS | DUE DATE | STATUS
| If approved, begin development of Transfer Blackboard shell (to be identified) | to be identified |  |  |  | 2020-10-08 | The team discussed the math alignment document, the program mapping process, and the multiple draft 2-/4-year program requirements. The team will meet again on December 2 with the intent to complete the math alignment document and the mapping process. All documents will be housed on an ACC site identified by Mary Jane.
| 2) If approved, complete agreement on college prep course (to be identified) | to be identified
| 3) Begin mapping of degree requirements (associate and baccalaureate degree) for 12 majors (to be identified) | to be identified

## Notes
Additional Meeting Notes
Suggested next meeting at TX ST RRC location, Avery Building
MATH pathways alignment -
Texas State remove old transfer information from website to eliminate confusion
increase enrollment in BAAS Program - specifically at the Round Rock Campus | Co-enrollment programs potential
1) engineering/engineering tech
ACC goals from session 1: early discussion of transfer and career goals to lead to intervention and support | 2) health sciences
Tx State goals from session 1: pipeline (engineering - but open to others) to transfer | 3) education
4) Business
difficulty in identifying concurrently enrolled students in real time. Depend on NSC and those reports are after the fact | 5) OWLS
Top careers ACC wants to identify: health sciences, engineering and engineering tech, manufacturing, business, education, OWLS, general studies | a) Information sessions - careers, opportunities for transfer
b) MOU
c) Bacalaureate pathway
Check in dates (potential): | d) math alignment
March 6, April 10, May 11-15, June 12, July 10, August 7
Future projects:
track what majors students began at ACC with, what major they had declared at point of transfer (at ACC and Texas State), and what major they are in one year later
With SB25 identify which courses students are taking that are not applying to the degree they are pursuing
Proposed meeting date
May 20, 1:30 at Texas State Round Rock Campus, Avery Conference Room

## Driver Diagram 90 days
OVERALL AIMS | PRIMARY DRIVERS | POSSIBLE ACTIONS
Improve outcomes for transfer students | Students taking the wrong math class | align math requirements
Faculty dialogues
S.M.A.R.T. AIM
Accumulating excess hours
Align math requirements and program maps to improve transfer of ACC students into the top ten majors at Texas State
Review program maps
Increased student debt
Schedule Texas State Advising @ ACC locations
Increased time to completion
develop communication strategy

## Driver Diagram - coenrollment
OVERALL AIMS | PRIMARY DRIVERS | POSSIBLE ACTIONS
Improve outcomes for transfer students | Navigate Bureaucracy | Align math requirements
MOU/Data Sharing Template
S.M.A.R.T. AIM
Lack of Curricular Alignment
Develop a framework to create co-enrollment and improved transfer for designated programs
Plan information sessions
Aligning Processes
Designate Tasks & Personnel
Identify Programs